## Task List
| Project Name | Drop Table Team Names
| Project Manager | Josh
| Date | 2021-02-23
| Version | 1
Task No. | Task Description | Task Owner | Dependency | Resources Needed | Task Status | Effort Required | Hour Estimate | Start Date | Estimated Completion | Finish Date | Notes
1 | Definition/Analysis Phase
1.1 | Team Charter | Complete | None | Slack/Zoom/Google Docs | Complete | Small |  |  |  | 2021-02-08
1.1.1 | Meet as group to establish team guidelines | Complete | None | Slack/Zoom/Google Docs | Complete | Small |  |  |  | 2021-02-08
1.1.2 | Create team charter document | Complete | None | Slack/Zoom/Google Docs | Complete | Small |  |  |  | 2021-02-08
1.2 | Project Plan | Complete | None | Google Docs, Excel | In Progress | Medium | 11 | 2021-02-15 | 2021-02-23
1.2.1 | Work Breakdown Structure | Josh | None | Excel | In Progress | Small | 2 | 2021-02-15 | 2021-02-23
1.2.2 | Define Increments | Charlie | None | Google Docs | In Progress | Small | 2 | 2021-02-15 | 2021-02-23
1.2.3 | Quality Plan | Martin | None | Google Docs | In Progress | Small | 2 | 2021-02-15 | 2021-02-23
1.2.4 | Risk Plan | Larry | None | Google Docs | In Progress | Small | 2 | 2021-02-15 | 2021-02-23
1.2.5 | Define Deliverable Schedule | Josh | None | Google Docs | In Progress | Small | 1 | 2021-02-15 | 2021-02-23
1.2.6 | Define Resources | Charlie | None | Google Docs | In Progress | Small | 1 | 2021-02-15 | 2021-02-23
1.2.7 | Define Organizational Structure | Josh | None | Google Docs | In Progress | Small | 1 | 2021-02-15 | 2021-02-23
1.3 | Vision Document | Larry | None | Google Docs | Unassigned | Medium | 8 | 2021-02-24 | 2021-03-09
1.3.1 | Document Stakeholder Vision | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-02-24 | 2021-03-09
1.3.2 | Document Problem | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-02-24 | 2021-03-09
1.3.3 | Identify Stakeholder Needs | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-02-24 | 2021-03-09
1.3.4 | Define Stakeholder Quality and Value | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-02-24 | 2021-03-09
2 | Design Phase
2.1 | Requirements Document | Charlie | None | Google Docs | Unassigned | Medium | 11 | 2021-03-10 | 2021-03-16
2.1.1 | Glossary | Unassigned | None | Google Docs | Unassigned | Small | 1 | 2021-03-10 | 2021-03-16
2.1.2 | Software Architecture | Unassigned | None | Google Docs | Unassigned | Small | 1 | 2021-03-10 | 2021-03-16
2.1.3 | Information Domain | Unassigned | None | Google Docs | Unassigned | Small | 1 | 2021-03-10 | 2021-03-16
2.1.4 | Functional Domain | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-03-10 | 2021-03-16
2.1.5 | Interfaces | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-03-10 | 2021-03-16
2.1.6 | Non-functional Requirements | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-03-10 | 2021-03-16
2.1.7 | Implementation Constraints | Unassigned | None | Google Docs | Unassigned | Small | 2 | 2021-03-10 | 2021-03-16
2.2 | Design Document | Wes | Requirements Document | Google Docs | Unassigned | Medium | 8 | 2021-03-24 | 2021-04-06
2.2.1 | Architecture | Unassigned | Requirements Document | Google Docs | Unassigned | Small | 2 | 2021-03-24 | 2021-04-06
2.2.2 | Static design | Unassigned | Requirements Document | Google Docs | Unassigned | Small | 2 | 2021-03-24 | 2021-04-06
2.2.3 | Class specifications | Unassigned | Requirements Document | Google Docs | Unassigned | Small | 2 | 2021-03-24 | 2021-04-06
2.2.4 | Dynamic design | Unassigned | Requirements Document | Google Docs | Unassigned | Small | 2 | 2021-03-24 | 2021-04-06
3 | Programming Phase
3.1 | Skeletal Increment | Unassigned | Requirements Document | Visual Studio Code, GitHub, mLab, Heroku | Unassigned | Large | 28 | 2021-02-24 | 2021-03-18
3.1.1 | Create GitHub repository, Heroku account | Wes | Requirements Document | GitHub | Unassigned | Small | 2 | 2021-02-24 | 2021-03-18
3.1.2 | Create mLab database | Josh | Requirements Document | mLab | Unassigned | Medium | 5 | 2021-02-24 | 2021-03-18
3.1.3 | Create application with create-react-app | Unassigned | Requirements Document | Visual Studio Code | Unassigned | Large | 10 | 2021-02-24 | 2021-03-18
3.1.4 | Write code to ensure messaging with Socket.io | Unassigned | Requirements Document | Visual Studio Code | Unassigned | Medium | 5 | 2021-02-24 | 2021-03-18
3.1.5 | Add Socket.io, MongoDB, Node.js libraries to application | Unassigned | Requirements Document | Visual Studio Code | Unassigned | Small | 2 | 2021-02-24 | 2021-03-18
3.1.6 | Add mLab URI to server code | Unassigned | Requirements Document | Visual Studio Code | Unassigned | Small | 2 | 2021-02-24 | 2021-03-18
3.1.7 | Push to GitHub and deploy to Heroku | Unassigned | Requirements Document | GitHub, Heroku | Unassigned | Small | 2 | 2021-02-24 | 2021-03-18
3.2 | Minimal Increment | Unassigned | Skeletal Increment | Visual Studio Code, GitHub, mLab, Heroku | Unassigned | Large | 65 | 2021-03-19 | 2021-04-08
3.2.1 | Write UI code with core visuals (basic grid, simple HTML table) | Unassigned | Skeletal Increment | Visual Studio Code | Unassigned | Large | 15 | 2021-03-19 | 2021-04-08
3.2.2 | Implement player data structure for database | Unassigned | Skeletal Increment | Visual Studio Code | Unassigned | Large | 10 | 2021-03-19 | 2021-04-08
3.2.3 | Develop client code to handle players and display info relevant to each user | Unassigned | Skeletal Increment | Visual Studio Code | Unassigned | Large | 10 | 2021-03-19 | 2021-04-08
3.2.4 | Implement turns and game state data structure for database | Unassigned | Skeletal Increment | Visual Studio Code | Unassigned | Large | 10 | 2021-03-19 | 2021-04-08
3.2.5 | Develop a game start/reset on the client | Unassigned | Skeletal Increment | Visual Studio Code | Unassigned | Medium | 5 | 2021-03-19 | 2021-04-08
3.2.6 | Implement core game logic in client and server code | Unassigned | Skeletal Increment | Visual Studio Code, GitHub, mLab, Heroku | Unassigned | Large | 15 | 2021-03-19 | 2021-04-08
3.3 | Target Increment | Unassigned | Design Document, Minimal Increment | Visual Studio Code | Unassigned | Large | 30 | 2021-04-09 | 2021-05-06
3.3.1 | Develop "game lobby" page | Unassigned | Design Document, Minimal Increment | Visual Studio Code | Unassigned | Medium | 5 | 2021-04-09 | 2021-05-06
3.3.2 | Polish UI | Unassigned | Design Document, Minimal Increment | Visual Studio Code | Unassigned | Medium | 10 | 2021-04-09 | 2021-05-06
3.3.3 | Ensure all game logic implemented correctly | Unassigned | Design Document, Minimal Increment | Visual Studio Code | Unassigned | Small | 5 | 2021-04-09 | 2021-05-06
3.3.4 | Polish logic to ensure all details are complete | Unassigned | Design Document, Minimal Increment | Visual Studio Code | Unassigned | Medium | 10 | 2021-04-09 | 2021-05-06
4 | System Test and Risk Analysis Phase
4.1 | Test Software | Unassigned | Various | Jest | Unassigned | Large | 27 | Ongoing | Ongoing
4.1.1 | Unit testing (skeletal increment) | Unassigned | Skeletal Increment | Jest | Unassigned | Medium | 3 | 2021-03-19 | 2021-03-23
4.1.2 | Integration testing (skeletal increment) | Unassigned | Skeletal Increment | Jest | Unassigned | Medium | 3 | 2021-03-19 | 2021-03-23
4.1.3 | End to end testing (skeletal increment) | Unassigned | Skeletal Increment | Jest | Unassigned | Medium | 3 | 2021-03-19 | 2021-03-23
4.1.4 | Unit testing (minimal increment) | Unassigned | Minimal Increment | Jest | Unassigned | Medium | 3 | 2021-04-09 | 2021-04-13
4.1.5 | Integration testing (minimal increment) | Unassigned | Minimal Increment | Jest | Unassigned | Medium | 3 | 2021-04-09 | 2021-04-13
4.1.6 | End to end testing (minimal increment) | Unassigned | Minimal Increment | Jest | Unassigned | Medium | 3 | 2021-04-09 | 2021-04-13
4.1.7 | Unit testing (target increment) | Unassigned | Target Increment | Jest | Unassigned | Medium | 3 | 2021-05-07 | 2021-05-11
4.1.8 | Integration testing (target increment) | Unassigned | Target Increment | Jest | Unassigned | Medium | 3 | 2021-05-07 | 2021-05-11
4.1.9 | End to end testing (target increment) | Unassigned | Target Increment | Jest | Unassigned | Medium | 3 | 2021-05-07 | 2021-05-11
4.2 | Risk Evaluation | Unassigned | Various | Google Docs | Unassigned | Large | 14 | 2021-02-24 | 2021-03-31
4.2.1 | Risk identification | Larry | None | Google Docs | Unassigned | Medium | 3 | 2021-02-24 | 2021-03-02
4.2.2 | Risk analysis | Unassigned | Risk identification | Google Docs | Unassigned | Medium | 3 | 2021-03-03 | 2021-03-09
4.2.3 | Risk planning | Unassigned | Risk analysis | Google Docs | Unassigned | Medium | 3 | 2021-03-10 | 2021-03-16
4.2.4 | Risk tracking | Unassigned | Risk planning | Google Docs | Unassigned | Small | 2 | 2021-03-17 | 2021-03-23
4.2.5 | Risk resolution | Unassigned | Risk tracking | Google Docs | Unassigned | Medium | 3 | 2021-03-24 | 2021-03-31
5 | Acceptance Phase
5.1 | Project Demonstrations | Unassigned | Various | Video Recording Software | Unassigned | Large | 15
5.1.1 | Prepare demonstration of skeletal increment | Unassigned | Skeletal Increment | Video Recording Software | Unassigned | Medium | 5 | 2021-03-19 | 2021-03-23
5.1.2 | Prepare demonstration of minimal increment | Unassigned | Minimal Increment | Video Recording Software | Unassigned | Medium | 5 | 2021-04-09 | 2021-04-13
5.1.3 | Prepare demonstration of target increment | Unassigned | Target Increment | Video Recording Software | Unassigned | Medium | 5 | 2021-05-07 | 2021-05-11

## Weekly Breakdown
Task No. | Task Description | Effort Required | Hour Estimate | Start Date | Estimated Completion
1 | Definition/Analysis Phase |  |  |  |  | Week #1
1.1 | Team Charter | Small |  |  |  | Task # | Task Description | Hour Estimate
1.1.1 | Meet as group to establish team guidelines | Small |  |  |  | 1.3.1 | Document Stakeholder Vision | 2
1.1.2 | Create team charter document | Small |  |  |  | 1.3.2 | Document Problem | 2
1.2 | Project Plan | Medium | 11 | 2021-02-15 | 2021-02-23 | 3.1.1 | Create GitHub repository, Heroku account | 2
1.2.1 | Work Breakdown Structure | Small | 2 | 2021-02-15 | 2021-02-23 | 3.1.2 | Create mLab database | 5
1.2.2 | Define Increments | Small | 2 | 2021-02-15 | 2021-02-23 | 4.2.1 | Risk identification | 3
1.2.3 | Quality Plan | Small | 2 | 2021-02-15 | 2021-02-23 |  | Total Hours | 14
1.2.4 | Risk Plan | Small | 2 | 2021-02-15 | 2021-02-23
1.2.5 | Define Deliverable Schedule | Small | 1 | 2021-02-15 | 2021-02-23 | Week #2
1.2.6 | Define Resources | Small | 1 | 2021-02-15 | 2021-02-23 | Task # | Task Description | Hour Estimate
1.2.7 | Define Organizational Structure | Small | 1 | 2021-02-15 | 2021-02-23 | 1.3.3 | Identify Stakeholder Needs | 2
1.3 | Vision Document | Medium | 8 | 2021-02-24 | 2021-03-09 | 1.3.4 | Define Stakeholder Quality and Value | 2
1.3.1 | Document Stakeholder Vision | Small | 2 | 2021-02-24 | 2021-03-09 | 3.1.4 | Write code to ensure messaging with Socket.io | 5
1.3.2 | Document Problem | Small | 2 | 2021-02-24 | 2021-03-09 | 3.1.3 | Create application with create-react-app | 10
1.3.3 | Identify Stakeholder Needs | Small | 2 | 2021-02-24 | 2021-03-09 | 3.1.5 | Add Socket.io, MongoDB, Node.js libraries to application | 2
1.3.4 | Define Stakeholder Quality and Value | Small | 2 | 2021-02-24 | 2021-03-09 | 4.2.2 | Risk analysis | 3
2 | Design Phase | [5 empty] | Total Hours | 24
2.1 | Requirements Document | Medium | 11 | 2021-03-10 | 2021-03-16
2.1.1 | Glossary | Small | 1 | 2021-03-10 | 2021-03-16 | Week #3
2.1.2 | Software Architecture | Small | 1 | 2021-03-10 | 2021-03-16 | Task # | Task Description | Hour Estimate
2.1.3 | Information Domain | Small | 1 | 2021-03-10 | 2021-03-16 | 2.1.1 | Glossary | 1
2.1.4 | Functional Domain | Small | 2 | 2021-03-10 | 2021-03-16 | 2.1.2 | Software Architecture | 1
2.1.5 | Interfaces | Small | 2 | 2021-03-10 | 2021-03-16 | 2.1.3 | Information Domain | 1
2.1.6 | Non-functional Requirements | Small | 2 | 2021-03-10 | 2021-03-16 | 2.1.4 | Functional Domain | 2
2.1.7 | Implementation Constraints | Small | 2 | 2021-03-10 | 2021-03-16 | 2.1.5 | Interfaces | 2
2.2 | Design Document | Medium | 8 | 2021-03-24 | 2021-04-06 | 2.1.6 | Non-functional Requirements | 2
2.2.1 | Architecture | Small | 2 | 2021-03-24 | 2021-04-06 | 2.1.7 | Implementation Constraints | 2
2.2.2 | Static design | Small | 2 | 2021-03-24 | 2021-04-06 | 3.1.6 | Add mLab URI to server code | 2
2.2.3 | Class specifications | Small | 2 | 2021-03-24 | 2021-04-06 | 4.2.3 | Risk planning | 3
2.2.4 | Dynamic design | Small | 2 | 2021-03-24 | 2021-04-06 |  | Total Hours | 16
3 | Programming Phase
3.1 | Skeletal Increment | Large | 28 | 2021-02-24 | 2021-03-18 | Week #4
3.1.1 | Create GitHub repository, Heroku account | Small | 2 | 2021-02-24 | 2021-03-18 | Task # | Task Description | Hour Estimate
3.1.2 | Create mLab database | Medium | 5 | 2021-02-24 | 2021-03-18 | 3.1.7 | Push to GitHub and deploy to Heroku | 2
3.1.3 | Create application with create-react-app | Large | 10 | 2021-02-24 | 2021-03-18 | 4.1.1 | Unit testing (skeletal increment) | 3
3.1.4 | Write code to ensure messaging with Socket.io | Medium | 5 | 2021-02-24 | 2021-03-18 | 4.1.2 | Integration testing (skeletal increment) | 3
3.1.5 | Add Socket.io, MongoDB, Node.js libraries to application | Small | 2 | 2021-02-24 | 2021-03-18 | 4.1.3 | End to end testing (skeletal increment) | 3
3.1.6 | Add mLab URI to server code | Small | 2 | 2021-02-24 | 2021-03-18 | 5.1.1 | Prepare demonstration of skeletal increment | 5
3.1.7 | Push to GitHub and deploy to Heroku | Small | 2 | 2021-02-24 | 2021-03-18 | 3.2.1 | Write UI code with core visuals (basic grid, simple HTML table) | 15
3.2 | Minimal Increment | Large | 65 | 2021-03-19 | 2021-04-08 | 4.2.4 | Risk tracking | 2
3.2.1 | Write UI code with core visuals (basic grid, simple HTML table) | Large | 15 | 2021-03-19 | 2021-04-08 |  | Total Hours | 33
3.2.2 | Implement player data structure for database | Large | 10 | 2021-03-19 | 2021-04-08
3.2.3 | Develop client code to handle players and display info relevant to each user | Large | 10 | 2021-03-19 | 2021-04-08 | Week #5
3.2.4 | Implement turns and game state data structure for database | Large | 10 | 2021-03-19 | 2021-04-08 | Task # | Task Description | Hour Estimate
3.2.5 | Develop a game start/reset on the client | Medium | 5 | 2021-03-19 | 2021-04-08 | 2.2.1 | Architecture | 2
3.2.6 | Implement core game logic in client and server code | Large | 15 | 2021-03-19 | 2021-04-08 | 2.2.2 | Static design | 2
3.3 | Target Increment | Large | 30 | 2021-04-09 | 2021-05-06 | 3.2.2 | Implement player data structure for database | 10
3.3.1 | Develop "game lobby" page | Medium | 5 | 2021-04-09 | 2021-05-06 | 3.2.3 | Develop client code to handle players and display info relevant to each user | 10
3.3.2 | Polish UI | Large | 10 | 2021-04-09 | 2021-05-06 | 4.2.5 | Risk resolution | 3
3.3.3 | Ensure all game logic implemented correctly | Medium | 5 | 2021-04-09 | 2021-05-06 |  | Total Hours | 27
3.3.4 | Polish logic to ensure all details are complete | Large | 10 | 2021-04-09 | 2021-05-06
4 | System Test and Risk Analysis Phase |  |  |  |  | Week #6
4.1 | Test Software | Large | 27 | Ongoing | Ongoing | Task # | Task Description | Hour Estimate
4.1.1 | Unit testing (skeletal increment) | Medium | 3 | 2021-03-19 | 2021-03-23 | 2.2.3 | Class specifications | 2
4.1.2 | Integration testing (skeletal increment) | Medium | 3 | 2021-03-19 | 2021-03-23 | 2.2.4 | Dynamic design | 2
4.1.3 | End to end testing (skeletal increment) | Medium | 3 | 2021-03-19 | 2021-03-23 | 3.2.4 | Implement turns and game state data structure for database | 10
4.1.4 | Unit testing (minimal increment) | Medium | 3 | 2021-04-09 | 2021-04-13 | 3.2.5 | Develop a game start/reset on the client | 5
4.1.5 | Integration testing (minimal increment) | Medium | 3 | 2021-04-09 | 2021-04-13 |  | Total Hours | 19
4.1.6 | End to end testing (minimal increment) | Medium | 3 | 2021-04-09 | 2021-04-13
4.1.7 | Unit testing (target increment) | Medium | 3 | 2021-05-07 | 2021-05-11 | Week #7
4.1.8 | Integration testing (target increment) | Medium | 3 | 2021-05-07 | 2021-05-11 | Task # | Task Description | Hour Estimate
4.1.9 | End to end testing (target increment) | Medium | 3 | 2021-05-07 | 2021-05-11 | 3.2.6 | Implement core game logic in client and server code | 15
4.2 | Risk Evaluation | Large | 14 | 2021-02-24 | 2021-03-31 | 4.1.4 | Unit testing (minimal increment) | 3
4.2.1 | Risk identification | Medium | 3 | 2021-02-24 | 2021-03-02 | 4.1.5 | Integration testing (minimal increment) | 3
4.2.2 | Risk analysis | Medium | 3 | 2021-03-03 | 2021-03-09 | 4.1.6 | End to end testing (minimal increment) | 3
4.2.3 | Risk planning | Medium | 3 | 2021-03-10 | 2021-03-16 | 5.1.2 | Prepare demonstration of minimal increment | 5
4.2.4 | Risk tracking | Small | 2 | 2021-03-17 | 2021-03-23 |  | Total Hours | 29
4.2.5 | Risk resolution | Medium | 3 | 2021-03-24 | 2021-03-31
5 | Acceptance Phase |  |  |  |  | Week #8
5.1 | Project Demonstrations | Large | 15 |  |  | Task # | Task Description | Hour Estimate
5.1.1 | Prepare demonstration of skeletal increment | Medium | 5 | 2021-03-19 | 2021-03-23 | 3.3.1 | Develop "game lobby" page | 5
5.1.2 | Prepare demonstration of minimal increment | Medium | 5 | 2021-04-09 | 2021-04-13 |  | Total Hours | 5
5.1.3 | Prepare demonstration of target increment | Medium | 5 | 2021-05-07 | 2021-05-11
Week #9
[6 empty] | Task # | Task Description | Hour Estimate
[6 empty] | 3.3.2 | Polish UI | 10
[7 empty] | Total Hours | 10
Week #10
[6 empty] | Task # | Task Description | Hour Estimate
[6 empty] | 3.3.3 | Ensure all game logic implemented correctly | 5
[7 empty] | Total Hours | 5
Week #11
[6 empty] | Task # | Task Description | Hour Estimate
[6 empty] | 3.3.4 | Polish logic to ensure all details are complete | 10
[6 empty] | 4.1.7 | Unit testing (target increment) | 3
[6 empty] | 4.1.8 | Integration testing (target increment) | 3
[6 empty] | 4.1.9 | End to end testing (target increment) | 3
[6 empty] | 5.1.3 | Prepare demonstration of target increment | 5
[7 empty] | Total Hours | 24